## Instructions
1. Overview
The MoSCoW list covers the key deliverables for an engagement to be successful and lists those deliverables in priority order within the following groups:
· Must Have – Deliverables that must be completed for the project to be successful.
· Should Have – Deliverables that should be completed for the project to have its maximum impact. Items that should be completed that are not completed during the initial engagement must be completed in a subsequent phase.
· Could Have – Deliverables that could be completed it the project plan has slack time and the project participants can use that slack time to advance or complete these deliverables. These deliverables should not be started if they can result in a time or cost overrun.
· Won’t Have – Deliverables that are identified as out of scope.
The MoSCoW list does not replace a formal project plan for larger project. It acts as a guide during the project’s execution to avoid discussion on deliverables that are not the primary focus of the engagement.
2. MoSCoW List Headings
The headings for the MoSCoW list cover the following:
· Actor – The primary actor who will use the deliverable. This can provide context on the use case for the deliverable.
· Goal – A short overview of the purpose of the deliverable.
· Description – A detailed description of the deliverable and its purpose in the project. Please note that this is not a replacement for a specification for large deliverables.
· MoSCoW Designation – Is this a Must Have, Could Have, Should Have, or Won’t Have deliverable of the project.
· Functional Area – What are of the project does this deliverable effect or is part of.
· Requestor – Deliverables are likely to be reviewed by many team members. However, this is the primary resource who is accountable to review the final deliverable.
· Dependencies – Is this deliverable dependent upon the completion of any other MoSCoW list item?
· Comments / Assumptions – Any comments or assumptions made when developing any portion of the MoSCoW item.

## MoSCoW List
Item # | Actor | Goal | Description | MoSCoW | Functional Area | Requestor | Dependencies | Comments/Assumptions
1 | Financial Advisor | Ability to add prospects. | Add new prospects to the CRM. | Must | Lead Process | Harry Potter |  | Minimum information includes • Name • Contact details
2 | Operations | Ability to gather prospective client information. | Ability to gather prospective client information in order to create a financial plan. | Must | Discovery Process | Hermoine Granger |  | Ability to capture the information to create the new financial plan. I deally this is captured in a web form to avoid data entry issues.
3 | Financial Planner | Ability to create the financial plan. | Ability to create the financial plan for the prospect. | Must | Account Funding | Hermoine Granger | MoSCoW 2 | Should we leverage our existing technologies or review a new financial planning capability?
4 | Financial Advisor | Review the proposed financial plan. | Ability for the advisor to review the financial plan and make adjustments to the plan before sending it to the prospective client. | Should | Account Funding | Doby Elf | Storyboard | Can the advisor update the plan without reverting back to the financial planner? How can compliance review any significant plan changes?
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25